## CostSheet
[8 empty] | Phase 1 | [8 empty] | Phase 2
# | Role | Base | Name | Resource | Position | Team | HeadCount | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | Total | GRAND Total | Cost per Unit | Total Cost (THB) | Sale Price per Unit | Total Revenue
[8 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jun
1 | Project Manager (PMO) | PT | Jirathitigorn Maneekord | PTT Digital | Senior Officer | AOU | 1 | 3 | 5 | 5 | 5 | 5 | 5 | 3 |  |  | 22 | 22 |  |  | 75 | 75 |  | 0 | 14000 | 1050000
2 | Functional Lead BA - FO-Chartering | PT | Thaninnut Siriphapsophon | PTT Digital | Senior Officer | AOU/O | 1 | [13 empty] | 8 | 8 |  | 0 | 14000 | 112000 | bar: Feb to Jul; Oct to Nov
3 | BA - FO-Physical | PT | Atawee Yongchooyot | PTT Digital | Senior Officer | AOU/O | 1 | 1 | 4 | 4 | 3 | 3 | 1 | 1 |  |  | 3 | 3 |  |  | 27 | 27 |  | 0 | 14000 | 378000
4 | BA - Mid Office | PT | Suriya Boonaramrueng | PTT Digital | Senior Officer | AOU/O | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 |  |  | 2 | 2 |  |  | 15 | 15 |  | 0 | 14000 | 210000
5 | BA - BO-AP, AR | PT | Kanoksak Tameeruksa | PTT Digital | Senior Officer | AOU/O | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 |  |  | 2 | 2 |  |  | 15 | 15 |  | 0 | 14000 | 210000
6 | BA - BO-Credit | PT | Kadesuda Tantisaereerat | PTT Digital | Officer | AOU/O | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 |  |  | 2 | 2 |  |  | 12 | 12 |  | 0 | 8500 | 102000
7 | BA - FO-Physical Storage | PT | Suchawalee Nandee | PTT Digital | Officer | AOU/O | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 2 | 2 |  |  | 10 | 10 |  | 0 | 8500 | 85000
8 | BA - FO-Derivatives | PT | Arithat Netipitchayapong | PTT Digital | Officer | AOU/O | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 2 | 2 |  |  | 10 | 10 |  | 0 | 8500 | 85000
9 | Legacy-SMT-SA | PT | Kavin Iamsila | PTT Digital | Senior Officer | ATA/S | 1 |  | 10 | 10 | 2 | 1 | 1 | 1 |  |  | 5 | 5 |  |  | 35 | 35 |  | 0 | 14000 | 490000
11 | Legacy-SMT-SA | PT | Thanapol Kuakamjad | PTT Digital | Officer | ATA/S | 1 |  | 10 | 5 | 2 | 1 | 1 | 1 |  |  | 5 | 5 |  |  | 30 | 30 |  | 0 | 8500 | 255000
13 | Infra. Admin (base on PTT Azure cloud) | PT | Thanakrit Yimyam | PTT Digital | Officer | IFM/O | 1 | Jul: 3 | 3 | 3 |  | 0 | 8500 | 25500
16 | Legacy - SAP Master | PT | Panita Yongyuth | PTT Digital | Senior Officer | AOU/API | 1 | [13 empty] | 7 | 7 |  | 0 | 14000 | 98000 | bar: Jan to Jul
17 | Legacy - SAP Master | PT | Boripan Chatree | PTT Digital | Officer | AOU/API | 1 | Jan: 1; Feb: 2; Mar: 1; Apr: 1; May: 1; Jun: 1; Jul: 1 | 8 | 8 |  | 0 | 8500 | 68000
18 | Legacy - RPA | PT | Sarun Anuchitkittikul | PTT Digital | Senior Officer |  | 1 | Jan: 1; Feb: 2; Mar: 2; Apr: 1; May: 1; Jun: 1; Jul: 1 | 9 | 9 |  |  | 14000 | 126000
19 | Legacy - RPA | PT | Narut Tripopnat | PTT Digital | Senior Officer |  | 1 | Jan: 1; Feb: 2; Mar: 1; Apr: 1; Jun: 1 | 6 | 6 |  |  | 14000 | 84000
20 | Legacy - RPA | PT | Kraisorn Khajornchaisak | PTT Digital | Senior Officer |  | 1 | [13 empty] | 8 | 8 |  |  | 14000 | 112000 | bar: Jan to Jul
21 | Legacy - RPA | PT | Amonrat Janfung | PTT Digital | Officer |  | 1 | Jan: 2; Feb: 2; Mar: 2; Apr: 1; May: 1; Jun: 1; Jul: 1 | 10 | 10 |  |  | 8500 | 85000
22 | Legacy - E-Ticket | PT | Atawee Yongchooyot | PTT Digital | Senior Officer | AOU/O | 1 | [14 empty] | 0 |  | 0 | 14000 | 0
23 | Legacy - Memorandum | PT | Ariya Kluankloi | PTT Digital | Senior Officer | TC | 1 | [14 empty] | 0 |  | 0 | 14000 | 0
24 | Legacy - Salesforce (Credit One) | PT | Thanawadee Tunrachanchai | PTT Digital | Senior Officer | APR/O | 1 | [13 empty] | 1 | 1 |  | 0 | 14000 | 14000 | bar: Jan
25 | Legacy - Credit Bureau | PT | Phonthep Jamroenkanokkul | PTT Digital | Officer | BTRD | 1 | [14 empty] | 0 |  | 0 | 8500 | 0
26 | Legacy - LCS | PT | Nawat Sangchot | PTT Digital | Officer | BTRD | 1 | [14 empty] | 0 |  | 0 | 8500 | 0
27 | Legacy - Data Lake | PT | Akarachai Atakulreka | PTT Digital | Senior Officer | ATA/B | 1 | [14 empty] | 0 |  | 0 | 14000 | 0
28 | Legacy - MoFi | PT | Pornchai Kukiatanan | PTT Digital | Senior Officer | BTRD | 1 | Jan: 3 | 3 | 3 |  | 0 | 14000 | 42000
29 | Legacy - FXBidding | PT | Jaruayporn Thongudom | PTT Digital | Senior Officer | BTRD | 1 | [14 empty] | 0 |  | 0 | 14000 | 0
30 | WSO2 | PT | Boripan Chatree | PTT Digital | Officer | AOU/API | 1 | [14 empty] | 0 |  | 0 | 8500 | 0
0
[21 empty] | Total Man-day | 292 |  |  | TOTAL | 3631500
3631500
0
0
Note on A5: T1 Account & Procurment
Note on A6: T1 Account & Procurment
Note on A21: T1 Account & Procurment

## Deliverable & Installment
Milestone | Deliverable | Deliver within (day)* | Installment (%)
Phase 1: Due date is count from the day receiving a purchase order
(1) SIT | 1) Project Detail Plan | 155 | 55
2) Functional Specification (if any)
3) SIT Script & Result
4) UAT Scenario
(2) Complete Phase 1 | 1) UAT Result | 230 | 25
2) Regression Test (if any)
3) Source Code / Security Scan
4) Deployment List
Phase 2: Due date is count from the day receiving PTT's notice letter to proceed with Phase 2
(3) Complete Phase 2 | 1) Functional Specification (if any) | 105 | 20
2) SIT Script & Result
3) UAT Script & Result
4) Source Code / Security Scan
5) Deployment List