## Resource
Team Information |  |  |  |  | Total Manday (Day)
No. | Name | Type | Role | Level | Planned (Day) | Manday Rate (Baht)
1 | Kongdech Hisavanich | Outsource | PM | Senior Officer | 32 | 14000 | 14000 | 448000
2 | Sasivimol Chinudomsuksakul | Outsource | BA | Senior Officer | 46 | 14000 | 14000 | 644000
3 | Kamonwan Oilkham | Outsource | BA | Officer | 61 | 8500 | 8500 | 518500
4 | Eakarin Pintafai | Outsource | Developer | Officer | 25 | 8500 | 8500 | 212500
5 | Wuttipong Inpalud | Outsource | Developer | Officer | 15 | 8500 | 8500 | 127500
6 | Natamon Jongbandan | Outsource | QA Team | Officer | 3 | 8500 | 8500 | 25500
0
1976000
Other Information |  | Total Amount (Baht)
1 | Hardware | -
2 | Software | -
3 | License | -
4 | Allowance | -
5 | ค่าดำเนินโครงการโดยที่ปรึกษาภายนอก (IBS Software) | -
6 | DevOps Service
หมายเหตุ ถ้ามีประเภทค่าใช้จ่ายอื่นๆ เพิ่มเติมใน Project เพิ่ม Row ได้
Total
Note on G3: Pimsupak Tammalakkhana: ให้ใส่ Cost หาก PM ไม่ทราบให้ว่างไว้
Note on B16: Pimsupak Tammalakkhana: ระบุค่าเดินทาง หาก Project ไหนต้องย่อยรายละเอียดการเดินทางแยก Sheet Declare มาอีกอัน

## Total
Digital Rev (Project Cost) | 1976000
ค่าเบี้ยเลี้ยง/ค่าเดินทาง | 0
Vendor Cost | 0
Total | 1976000
ค่าเดินทาง | จำนวนครั้ง | ครั้งละ | รวมค่าเดินทาง
Location A |  |  | 0
Location B |  |  | 0
Location C |  |  | 0
|  | Total | 0
ค่าเบี้ยเลี้ยง | จำนวนครั้ง | ครั้งละ | รวมค่าเบี้ยเลี้ยง
MR A |  | 600 | 0
MR B |  | 600 | 0
MR C |  | 600 | 0
|  | Total | 0
งวดการชำระเงิน PTTEP >> PTT Digital | % | จำนวนเงิน |  | Digital Cost + Vendor | 1976000
งวดที่ 1 : Kick off | 20% | 395200 |  | Margin | 0
งวดที่ 2 : Requirement Gathering | 30% | 592800
งวดที่ 3 : User Acceptance Test | 30% | 592800 |  | % Margin | 0%
งวดที่ 4 : Go-live | 20% | 395200
| 100% | 1976000
งวดการชำระเงิน PTT DIGITAL >> Vendor | % | จำนวนเงิน
งวดที่ 1 : Requirement & Design | 40% | 0
งวดที่ 2 : Golive # 1 | 30% | 0
งวดที่ 3 : Golive # 2 | 30% | 0
| 100% | 0

## PTTDigital_Manday
Project : PJR-PTTEP-Discrepancy and Write-off System (DiW) for Corporate
(ระยะเวลาโครงการ 280 วัน) |  |  | Sr1 | Sr1 | Of1 | Of1 | Of1 | Of1 | Sr1 | Of1
Phase | Details | Deliverables | PM | BA | BA | Developer | Developer | QA | Tech. Review | App. Support
|  |  | Kongdech H. | Sasivimol C | Kamonwan O | Eakkarin P | Wuttipong | Natamon J | Name | Name
Project Planning | Pre-pare proposal & procument process | Proposal, Kick-off Presentation, Project Plan | 5 | 2
| Project Assessment and Planing |  | 3 | 6
| Project Kick-off |  | 1 | 2
Implement, Testing and Deployment forPhase 1A | Weekly progress and Issue management (11 months) - Weekly Progress report - Internal progress tracking - Issue log management | Weekly report | 20 | 2
Requirement Gethering and Design | DDR – Damage discrepancy report | SRS & FSD Document, SRS & FSD Sign-Off
| - Intergrattion Module with GCP |  |  | 0.5 | 1
| - Group,Roles and Authorization by country/asset/plant |  |  | 0.5 | 1
| - Table, backend screen, Logic |  |  | 0.5 | 1
| - Workflow |  |  | 0.5 | 1
| - Email Notification |  |  | 0.5 | 0.5
| - Generate PDF |  |  | 0.5 | 0.5
| - Portal form (Update solution) |  |  | 0.5 | 0.5
| - Dashboard |  |  | 0.5 | 0.5
| - Schedule job (reminder email) |  |  | 0.5 | 0.5
Inteface to GCP
| - Settle solution with GCP |  |  | 1 | 2
| - Intergrate with GCP |  |  | 1 | 2
| - Prepare data object |  |  | 0.5 | 1
| - Logic |  |  | 0.5 | 1
Prepare document and confirm
| Prepare SRS and confirmation |  |  | 2 | 3
| System design with DEV team |  |  | 1.5 | 1.5
| Prepare FSD and confirmation |  |  | 2 | 3
| Milestone 2/4 : SRS & FSD Sign-Off |  | 0.5
Implement, Testing and Deployment | Sprint 1 - DDR – Damage discrepancy report
Solution development & Unit Test
| - Intergrate data from GCP |  |  |  |  | 3
| - Group,Roles and Authorization by country/asset/plant |  |  |  |  | 2
| - Table, backend screen, Logic |  |  |  |  | 4
| - Workflow |  |  |  |  | 4
| - Email Notification |  |  |  |  | 2
| - Generate PDF |  |  |  |  | 2
| - Portal form (Update solution) |  |  |  |  | 2
| - Dashboard |  |  |  |  | 2
| - Schedule job (reminder email) |  |  |  |  | 2
Prepare Sprint demo and SIT Script
| - Prepare SIT script |  |  | 1 | 2
| - Excute SIT |  |  | 1 | 2
| - Prepare demo presentation (with UAT senario) |  |  | 1 | 2
UAT assistance and Product Backlog update
| - Perform demo feature and Execute UAT |  |  | 1 | 2 | 2
| - Update and Summarize Product backlog |  |  |  | 0.5
Sprint 2 - Inteface to GCP
Solution development & Unit Test
| - Intergrate with GCP | [5 empty] | 4
| - Logic | [5 empty] | 8
Prepare Sprint demo and SIT Script
| - Prepare SIT script |  |  | 0.5 | 2
| - Excute SIT |  |  | 0.5 | 4
| - Prepare demo presentation (with UAT senario) |  |  | 1 | 2
UAT assistance and Product Backlog update
| - Perform demo feature and Execute UAT |  |  | 1 | 2 |  | 3
| - Update and Summarize Product backlog |  |  |  | 0.5
SIT & UAT with SHANA | RT/SIT Component |  |  | 1 | 2
| Performance Test |  |  | 1 | 2
| UAT execution |  |  | 1 | 2
| Product Backlog update |  |  |  | 1
Training & Final UAT | - Summary UAT Script & Review |  |  | 1
- Deliver all backlog
| - Milestone 3/4 : UAT Sign-Off | UAT Sign-off | 0.5
| - Develop User guides, Admin Guides |  |  | 1 | 3
| - Train the Trainer |  |  | 2 | 2
Deployment | QA Process | Go-live Sign-off |  | 1 | 2 |  |  | 3
| Go-live Comunication & preparation (CRQ request) |  | 1 | 2 | 3
| Go-Live |  |  | 1 | 1
| Milestone 4/4 : Go-Live Sign-Off |  | 0.5
Support and Project Closure | After go-live support - Issue Clarification and Summary | Project Issue log (updat issue from go-live support) |  | 1 | 3
| Project Closure & Presentation - Prepare Project closure presentation - Arrange the meeting | Project closure presentation | 0.5 | 2 | 1
Total |  |  | 32 | 46 | 61 | 25 | 15 | 3 | 0 | 0
Digital Rev
Note : | Junior = 8,500 per day | Rev / Day | 14000 | 14000 | 8500 | 8500 | 8500 | 8500 | 14000 | 8500
| Senior = 14,000 per day | Rev (Project Cost) | 448000 | 644000 | 518500 | 212500 | 127500 | 25500 | 0 | 0 | 1976000
1976000

## Sheet1 (hidden)
Project : PJR-PTTEP-Discrepancy and Write-off System (DiW) for Corporate
(ระยะเวลาโครงการ 280 วัน) |  |  | Sr1 | Sr1 | Sr1 | Sr1 | Sr1 | Sr1 | Of1 | Sr1 | Of1
Phase | Details | Deliverables | PM | BA | SA | SA | Developer | Developer | QA | Tech. Review | App. Support
|  |  | Kongdech H. | Sasivimol C | Penpitcha O | Kamonwan O | Eakkarin P | Wuttipong | Natamon J | Name | Name
Project Planning | Pre-pare proposal & procument process | Proposal, Kick-off Presentation, Project Plan | 4 | 4
| Project Assessment and Planing |  | 6 | 6 | 2 | 2
| Project Kick-off |  | 1 | 2 | 0.5 | 0.5
Implement, Testing and Deployment forPhase 1A | Weekly progress and Issue management (14 months) - Weekly Progress report - Internal progress tracking - Issue log management | Weekly report | 20 | 4
Sprint 1 - DDR – Damage discrepancy report
Gather requirement/ Design
| - Intergrate data from GCP |  |  | 2 |  | 4
| - Group,Roles and Authorization by country/asset/plant |  |  | 1 |  | 2
| - Table, backend screen, Logic |  |  | 2 |  | 4
| - Workflow |  |  | 2 |  | 4
| - Email Notification |  |  | 2 |  | 3
| - Generate PDF |  |  | 1 |  | 2
| - Portal form (Update solution) |  |  | 2 |  | 4
| - Dashboard |  |  | 1 |  | 2
| - Schedule job (reminder email) |  |  | 1 |  | 2
Solution development & Unit Test
| - Intergrate data from GCP | [5 empty] | 3
| - Group,Roles and Authorization by country/asset/plant | [5 empty] | 2
| - Table, backend screen, Logic | [5 empty] | 5
| - Workflow | [5 empty] | 4
| - Email Notification | [6 empty] | 2
| - Generate PDF | [6 empty] | 4
| - Portal form (Update solution) | [6 empty] | 5
| - Dashboard | [6 empty] | 2
| - Schedule job (reminder email) | [6 empty] | 2
Prepare Sprint demo and SIT Script
| - Prepare SIT script |  |  | 1 | 4
| - Excute SIT |  |  | 1.5 | 5
| - Prepare demo presentation (with UAT senario) |  |  | 1 | 3
UAT assistance and Product Backlog update
| - Perform demo feature and Execute UAT |  |  | 2 | 2 | 2 | 1 | 1
| - Update and Summarize Product backlog |  |  |  | 0.5 | 0.5
Sprint 2 - IDR – Inventory discrepancy report
Gather requirement/ Design
| - Intergrate data from GCP |  |  | 1 | 3
| - Group,Roles and Authorization by country/asset/plant |  |  | 1 | 2
| - Table, backend screen, Logic |  |  | 1 | 3
| - Workflow |  |  | 1 | 2
| - Email Notification |  |  | 1 | 3
| - Generate PDF |  |  | 1 | 3
| - Portal form (Update solution) |  |  | 1 | 3
| - Dashboard |  |  | 1 | 2
| - Schedule job (reminder email) |  |  | 1 | 2
Solution development & Unit Test
| - Intergrate data from GCP | [5 empty] | 3
| - Group,Roles and Authorization by country/asset/plant | [5 empty] | 2
| - Table, backend screen, Logic | [5 empty] | 3
| - Workflow | [5 empty] | 3
| - Email Notification | [6 empty] | 2
| - Generate PDF | [6 empty] | 4
| - Portal form (Update solution) | [6 empty] | 5
| - Dashboard | [6 empty] | 2
| - Schedule job (reminder email) | [6 empty] | 2
Prepare Sprint demo and SIT Script
| - Prepare SIT script |  |  | 1 |  | 3
| - Excute SIT |  |  | 1.5 |  | 5
| - Prepare demo presentation (with UAT senario) |  |  | 1 |  | 3
UAT assistance and Product Backlog update
| - Perform demo feature and Execute UAT |  |  | 2 | 2 | 2 | 1 | 1
| - Update and Summarize Product backlog |  |  |  | 0.5 | 0.5
| - Milestone 1/6 : SRS & FSD #1 Sign-Off | SRS & FSD Sign-off | 1
Training and Final UAT
| - Summary UAT Script & Review |  |  | 1 | 2
| - Deliver all backlog |  |  |  | 1
| - Milestone 2/6 : UAT#1 Sign-Off | UAT Sign-off | 1
| - Develop User guides, Admin Guides |  |  |  | 2
| - Train the Trainer |  |  | 1 | 1
Go-live Phase 1
| - QA Process |  |  | 1 | 2 |  |  |  | 3
| - Go-live Comunication & preparation (CRQ request) |  | 0.5 | 1 | 1 | 1
| - Go-Live |  |  | 0.5 | 1 | 1
| - Milestone 3/6 : Go-Live#1 Sign-Off | Go-live Sign-off | 1
| Weekly progress and Issue management (14 months) - Weekly Progress report - Internal progress tracking - Issue log management | Weekly report | 30 | 8
Sprint 3 - Write-off
Gather requirement/ Design
| - Intergrate to AI for Inventory (Connect to endpoint, logic, mapping data) |  |  | 2 | 3
| - Intergrate data from GCP |  |  | 1 | 2.5
| - Group,Roles and Authorization by country/asset/plant |  |  | 1 | 2
| - Table, backend screen, Logic |  |  | 1 | 2.5
| - Workflow |  |  | 1 | 2
| - Email Notification |  |  | 1 | 2
| - Generate PDF |  |  | 1 | 3
| - Portal form (Update solution) |  |  | 1 | 2
| - Dashboard |  |  | 1 | 3
| - Schedule job (reminder email) |  |  | 1 | 2
Solution development & Unit Test
| - Intergrate to AI for Inventory (Connect to endpoint, logic, mapping data) | [5 empty] | 6
| - Intergrate data from GCP | [5 empty] | 4
| - Group,Roles and Authorization by country/asset/plant | [5 empty] | 2
| - Table, backend screen, Logic | [5 empty] | 7
| - Workflow | [5 empty] | 4
| - Email Notification | [6 empty] | 2
| - Generate PDF | [6 empty] | 5
| - Portal form (Update solution) | [6 empty] | 4
| - Dashboard | [6 empty] | 3
| - Schedule job (reminder email) | [6 empty] | 2
Prepare Sprint demo and SIT Script
| - Prepare SIT script |  |  | 2 |  | 4
| - Excute SIT |  |  | 2 |  | 5
| - Prepare demo presentation (with UAT senario) |  |  | 2 |  | 6
UAT assistance and Product Backlog update
| - Perform demo feature and Execute UAT |  |  | 3 | 2 | 3 | 2 | 2
| - Update and Summarize Product backlog |  |  |  | 1 | 1
Sprint 4 - Inteface to GCP
Gather requirement/ Design
| - Settle solution with GCP |  |  | 2 | 4
| - Intergrate with GCP |  |  | 1.5 | 3
| - Prepare data object |  |  | 2 | 5
| - Logic |  |  | 1.5 | 4
Solution development & Unit Test
| - Intergrate with GCP | [5 empty] | 4
| - Logic | [5 empty] | 8
Prepare Sprint demo and SIT Script
| - Prepare SIT script |  |  | 0.5 |  | 3
| - Excute SIT |  |  | 0.5 |  | 5
| - Prepare demo presentation (with UAT senario) |  |  | 1 |  | 3
UAT assistance and Product Backlog update
| - Perform demo feature and Execute UAT |  |  | 3 |  | 3 | 1 | 1
| - Update and Summarize Product backlog |  |  |  | 0.5 | 0.5
| - Milestone 4/6 : SRS & FSD #2 Sign-Off | SRS & FSD Sign-off | 1
Training and Final UAT
| - Summary UAT Script & Review |  |  | 1 | 2
| - Deliver all backlog |  |  |  | 1
| - Milestone 5/6 : UAT#2 Sign-Off | UAT Sign-off | 1
| - Develop User guides, Admin Guides |  |  |  | 2
| - Train the Trainer |  |  | 1 | 1
Go-live Phase 2
| - QA Process |  |  | 1 | 2 |  |  |  | 3
| - Go-live Comunication & preparation (CRQ request) |  | 0.5 | 1 | 1 | 1
| - Go-Live |  |  | 0.5 | 1 | 1
| - Milestone 6/6 : Go-Live#2 Sign-Off | Go-live Sign-off | 1
Go-live support and Project Closure | After go-live support - Issue Clarification and Summary | Project Issue log (updat issue from go-live support) |  | 3 | 5 | 5
| Project Closure & Presentation - Prepare Project closure presentation - Arrange the meeting | Project closure presentation | 1 | 3
Total |  |  | 69 | 105 | 111 | 88 | 65 | 51 | 6 | 0 | 0
Digital Rev
Note : | Junior = 8,500 per day | Rev / Day | 14000 | 14000 | 8500 | 8500 | 8500 | 8500 | 8500 | 14000 | 8500
| Senior = 14,000 per day | Rev (Project Cost) | 966000 | 1470000 | 943500 | 748000 | 552500 | 433500 | 51000 | 0 | 0 | 5164500
5164500

## Vendor Cost
Project : -
Vendor : -
Order | Description | Cost
1 | Implement Cost | -
| Total | 0
Discount
| Grand Total | 0
** ราคานี้ยังไม่รวม Vat 7% **

## Plan
|  | 2025 | [8 empty] | 2026
Project : Discrepancy and Write off System (DiW) for Malausia |  | June |  |  |  | July |  |  |  |  | Month 01 |  |  |  | Month 02 |  |  |  | Month 03 |  |  |  |  | Month 01 |  |  |  | Month 02 |  |  |  | Month 03 |  |  |  | Month 04 |  |  |  |  | Month 05 |  |  |  | Month 06 |  |  |  |  | Month 7 |  |  |  | Month 11 |  |  |  | Month 12
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5
Phase I : Project Management | bar: Month 01 W3 to Month 01 W4
1.1 | Prepare proposal & procument process | Month 01 W3: 3; Month 01 W4: 3
1.2 | Project assessment and planning | Month 01 W3: 3
1.3 | Project Kick-off | Month 02 W1: 3
1.4 | Milestone 1/4 : SRS & FSD Sign-Off | Month 02 W1: 3
1.5 | Weekly progress update | bar: Month 02 W1
Phase II : Requirement Gethering and Design | bar: Month 02 W1 to Month 02 W2
2.1 | DDR Gather requirement/ Design | Month 02 W1: 3; Month 02 W2: 3
2.2 | Inteface to GCP(DiW -> GCP) Gather requirement/ Design | Month 02 W2: 3
2.3 | Prepare SRS and confirmation | bar: Month 02 W2
2.4 | System design with DEV team | bar: Month 02 W2 to Month 02 W3
2.5 | Prepare FSD and confirmation | bar: Month 02 W3
2.6 | Milestone 2/4 : SRS & FSD Sign-Off | bar: Month 02 W3
Phase III : Implement
3.1 | Sprint 1 - DDR – Damage discrepancy report | bar: Month 02 W2 to Month 03 W3
3.1.1 | Solution development and UT/RT/SIT | bar: Month 02 W2 to Month 02 W4
3.1.2 | Sprint demo and pre-pare UAT | bar: Month 02 W4 to Month 03 W1
3.1.3 | UAT assistance and Product Backlog update | bar: Month 03 W2 to Month 03 W3
3.2 | Sprint 2 - Inteface to GCP | bar: Month 03 W2 to Month 04 W4
3.2.1 | Solution development and UT/RT/SIT | Month 03 W2: 3; Month 03 W3: 3; Month 03 W4: 3
3.2.2 | Sprint demo and pre-pare UAT | Month 03 W4: 3; Month 04 W1: 3; Month 04 W2: 3
3.2.3 | UAT assistance and Product Backlog update | Month 04 W3: 3; Month 04 W4: 3
Phase IV : SIT & UAT with SHANA | bar: Month 02 W2 to Month 04 W4
4.1 | RT/SIT Component | Month 02 W2: 3; Month 02 W3: 3; Month 02 W4: 3
4.2 | Performance Test | Month 03 W1: 3; Month 03 W2: 3; Month 03 W3: 3; Month 03 W4: 3; Month 04 W1: 3
4.3 | UAT | Month 04 W2: 3; Month 04 W3: 3; Month 04 W4: 3
4.4 | Product Backlog update | Month 04 W2: 3; Month 04 W3: 3; Month 04 W4: 3
Phase V : Training & Final UAT | bar: Month 04 W5 to Month 06 W1
5.1 | Summary UAT Script & Review | Month 04 W5: 3; Month 05 W1: 3
5.2 | Deliver all backlog | Month 05 W1: 3; Month 05 W2: 3
5.3 | Milestone 3/4 : UAT Sign-Off | Month 05 W2: 3
5.4 | Develop User guides, Admin Guides | Month 05 W2: 3; Month 05 W3: 3
5.5 | Train the Trainer | Month 05 W3: 3; Month 05 W4: 3; Month 06 W1: 3
Phase VI : Deployment | bar: Month 05 W4 to Month 06 W3
6.1 | QA Process | Month 05 W4: 3; Month 06 W1: 3
5.2 | Go-live Comunication & preparation | Month 06 W1: 3; Month 06 W2: 3; Month 06 W3: 3
6.3 | Go-Live | Month 06 W3: 3
6.4 | Milestone 4/4 : Go-Live#1 Sign-Off | Month 06 W3: 3
Phase VII : Support after Golive | bar: Month 06 W3 to Month 7 W1
7.1 | Support After Go-Live | Month 06 W3: 3; Month 06 W4: 3; Month 06 W5: 3; Month 7 W1: 3
7.2 | Project Closure & Presentation | Month 7 W1: 3

## Vendor MD (hidden)
PTTEP FaFE Phase 4 | Resource | Summary | Solution Consultant (EmpowerAll) | Technical Consultant (Empower All) | Junior Technical Consultant (Empower All)
Name |  |  | TBA | TBA | TBA
Rate |  |  | 30240 | 22680 | 12060
Initiate Stage
Gathering Requirement
Research Solution
Business Development Stage
Prepare Team member project
Define Scope of work
Prepare Stage
Pre-pare proposal & procument process
Project Assessment and Planing
Project Kick-off
Create Stage
Sprint 1 - Standalone module |  |  | 0 | 0 | 0
Gather requirement/ Design
Solution development & Unit Test
Sprint demo, SIT/UAT assistance and Product Backlog update
Sprint 2 - Memo module |  |  | 0 | 0 | 0
Gather requirement/ Design
Develop issue from previous backlog
Solution development & Unit Test
Sprint demo, SIT/UAT assistance and Product Backlog update
Sprint 3 - TEPM Expansion |  |  | 0 | 0 | 0
Gather requirement/ Design
Develop sprint backlog
Solution development & Unit Test
Sprint demo, SIT/UAT assistance and Product Backlog update
Sprint 4 - RFS module |  |  | 0 | 0 | 0
Gather requirement/ Design
Develop issue from previous backlog
Solution development & Unit Test
Sprint demo, SIT/UAT assistance and Product Backlog update
Sprint 5 - Data bridging |  |  | 0 | 0 | 0
SAP Integration RO, Contract, Enhance PO/SO
Gather requirement/ Design
Develop sprint backlog
Solution development & Unit Test
Sprint demo, SIT/UAT assistance and Product Backlog update
Sprint 6 - GRO module |  |  | 0 | 0 | 0
Gather requirement/ Design
Develop issue from previous backlog
Solution development & Unit Test
Sprint demo, SIT/UAT assistance and Product Backlog update
Sprint 7 - IDR module |  |  | 0 | 0 | 0
Gather requirement/ Design
Develop issue from previous backlog
Solution development & Unit Test
Sprint demo, SIT/UAT assistance and Product Backlog update
Sprint 8 - DDR module |  |  | 0 | 0 | 0
Gather requirement/ Design
Develop issue from previous backlog
Solution development & Unit Test
Sprint demo, SIT/UAT assistance and Product Backlog update
Sprint 9- Write-off module |  |  | 0 | 0 | 0
Gather requirement/ Design
Develop issue from previous backlog
Solution development & Unit Test
Sprint demo, SIT/UAT assistance and Product Backlog update
Sprint 10 - Configure SAP Integration IDR, DDR, Write off |  |  | 0 | 0 | 0
Gather requirement / Provide logic / design
Develop issue from previous backlog
Solution development & Unit Test
Sprint demo, SIT/UAT assistance and Product Backlog update
Sprint 11 - Temp. Storage module |  |  | 0 | 0 | 0
Gather requirement/ Design
Develop issue from previous backlog
Solution development & Unit Test
Sprint demo, SIT/UAT assistance and Product Backlog update
Transition Stage
Deliver all backlog
Develop User guides, Admin Guides
User Training
Project administration & Weekly Status reports
Go-live Comunication & preparation
Go-Live & Early Live Support
Close Stage
Project Closure report and presentation
Summary Manday |  |  | 0 | 0 | 0
Sub-Total |  |  | 0 | 0 | 0
Total Estimate (ex VAT) |  | 0 |  |  |  | 0