## Resource
Team Information |  |  |  |  | Total Manday (Day)
No. | Name | Type | Role | Level | Planned (Day) | Manday Rate (Baht)
1 | Wannaporn Jaemklam | Outsource | PM/BA/Tester | Senior Officer | 30 | 14000 | 14000 | 420000
2 | Wissanu Tangtrongkijwong | Outsource | Developer | Senior Officer | 30 | 14000 | 8500 | 255000
3 | Niti Wisatchanam | Outsource | Developer | Officer | 37 | 8500 | 14000 | 518000
4 | Thanadol Lerdsakcharoenkul | IT Security Engineer | Security | Officer | 3 | 8500 |  | 1193000
[5 empty] | 100 | 1180000
Other Information |  | Total Amount (Baht)
1 | Hardware | -
2 | Software | -
3 | License | -
4 | Allowance | -
5 | ค่าดำเนินโครงการโดยที่ปรึกษาภายนอก | -
6 | DevOps Service
หมายเหตุ ถ้ามีประเภทค่าใช้จ่ายอื่นๆ เพิ่มเติมใน Project เพิ่ม Row ได้
1000000
1190000
[7 empty] | Total | 2190000
Note on G3: Pimsupak Tammalakkhana: ให้ใส่ Cost หาก PM ไม่ทราบให้ว่างไว้
Note on B17: Pimsupak Tammalakkhana: ระบุค่าเดินทาง หาก Project ไหนต้องย่อยรายละเอียดการเดินทางแยก Sheet Declare มาอีกอัน

## Total
โครงการ ENH-PTTEP-iCMS 2026 Enhancement | ระยะเวลาโครงการ 172 วัน
Digital Rev (BD Phase) | 21000
Digital Rev (Development Phase) | 1159000
ค่าเบี้ยเลี้ยง/ค่าเดินทาง | 0
Vendor Cost + 10 %
Total | 1180000
ค่าเดินทาง | จำนวนครั้ง | ครั้งละ | รวมค่าเดินทาง
N/A
Total
ค่าเบี้ยเลี้ยง | จำนวนครั้ง | ครั้งละ | รวมค่าเบี้ยเลี้ยง
N/A
Total
งวดการชำระเงิน PTT >> PTT Digital | % | จำนวนเงิน
งวดที่ 1 : Requirement & Design | 30% | 0 |  | Cost Performance
งวดที่ 2 : Golive | 70% | 0
| 100% | 0
|  |  |  | Digital Cost + Vendor | #REF!
|  |  |  | Add Overhead | #REF!
งวดการชำระเงิน PTT Digital >> Vendor | % | จำนวนเงิน |  | Margin | #REF!
|  |  |  | % Margin | #REF!

## DGT_Manday
โครงการ ENH-PTTEP-iCMS 2026 Enhancement
ระยะเวลาโครงการ 172 วัน |  |  | Sr1 | Sr1 | Sr1 | Sr1 | Of1
Phase | Details | Deliverables | PM | BA/Tester | Sr. Developer | Developer | Security
|  |  | Wannaporn Jaemklam | Wannaporn Jaemklam | Wissanu Tangtrongkijwong | Niti Wisatchanam | Thanadol Lerdsakcharoenkul
Business Development | Gather Initial Requirements | Proposal, TOR |  | 1
| Create Proposal |  | 0.5
Project Management | Kick-Off Meeting |  | 0.25
| Create Project Plan, Other Plans and Integrate to Project Plan |  | 0.5
| Project Monitoring (23*0.125) |  | 3
| Bi-Weekly Update Progress (10*0.25) |  | 3
Requirement Development | Get Requirement |  |  | 2 | 1
| Confirm Requirement |  |  | 0.5
Design | Review Requirment & Design Spec | Sign-Off Requirement & Design Specification |  | 2
| Confirm Requirment & Design Spec |  |  | 0.5
| Sign off Requirement & Design Specification |  | 0.25
Software Development | Prepare and setup Dev, SIT, UAT Environment |  |  | 0.5
Development + Unit Test
| PPS_001 ดำเนินการปรับปรุงการแสดงผลข้อมูลในระบบ โดยเปลี่ยนการแสดงผลจาก Major เป็น Discipline-Based JCP และจาก Minor เป็น Job-Based JCP ในทุกส่วนที่มีการแสดงข้อมูล - 16 Menu สำหรับพนักงาน - 2 Menu สำหรับ Admin - 13 Report - 1 Dashboard |  |  |  | 2.5 | 4
| PPS_002 ดำเนินการปรับปรุงการจัดเก็บข้อมูล Model สำหรับ Common Competency |  |  |  | 1
| PPS_003 ดำเนินการปรับปรุงการกำหนดค่า Mandatory และ Target Score สำหรับ Common Competency |  |  |  | 1
| PPS_004 ดำเนินการปรับปรุงระบบให้รองรับการ Mapping ข้อมูล Evidence ของ Soft Skill ไปยัง Common Competency |  |  |  | 2
| PPS_005 ดำเนินการปรับปรุงการแสดงผลบนหน้าจอ, Report และ Dashboard ภายในระบบ เพื่อรองรับการประเมินด้วย Model Common Competency |  |  |  | 18.5 | 28
Menu ที่ต้องปรับปรุงมีดังนี้ - Self Assessment – Staff (2.5,3) - Salf Assessment – Summary (0, 0.5) - ICDP – Staff (1,2) - Add Unplanned ICDP (1,0) - Self Assessment – Export Excel (0.5,2) - Salf Assessment - Export ICDP (0.5,2) - RP015 Technical & Soft Skill Calibration Report (For Employee) (0.5,2) - RP008 Individual Proficiency Report (GG & PE Only) (1,0.5) - Review Assessment & Plan ICDP (0.5,1) - Review Assessment & Plan ICDP – Multiple Review (1,5) - Track Your Team Progress ICDP (0.5,1)
Menu สำหรับ Admin ที่ต้องปรับปรุงมีดังนี้ - Import JFM Calibration (1,0) - Import Panel Assessment (1,0)
Report สำหรับ Admin ที่ต้องปรับปรุงมีดังนี้ - RP012 Promotion Candidate Shortlist Report (1,0.5) - RP012 Promotion Candidate Shortlist Report (New) (1,0.5) - RP015 Technical & Soft Skill Calibration Report (For Admin) (0.5,3) - RP015 Technical & Soft Skill Calibration Report (SA) (1,3) - RP016 Competency Inventory Report (1,0.5) - RP018 ICDP Report (1,1)
Dashboard ที่ต้องปรับปรุงมีดังนี้ - Top 10 of Gap Ranking Competency (2,0.5)
| PPS_006 ดำเนินการปรับปรุงสิทธิ์สำหรับ Technical Reviewer โดยกำหนดให้ไม่สามารถดำเนินการประเมินเอกสารในส่วนของ Common Competency ของพนักงานได้ |  |  |  | 0.5 | 1
| PPS_007 ดำเนินการปรับปรุงสิทธิ์สำหรับ Technical Reviewer โดยกำหนดให้ไม่สามารถวางแผน ICDP ให้กับพนักงานได้ ทั้งในส่วนของ Common Competency และ Technical Competency |  |  |  | 0.5 | 1
| PPS_008 ดำเนินการปรับปรุงคู่มือการใช้งาน ให้สอดคล้องกับรูปแบบการประเมินปัจจุบัน |  |  | 3
Testing
| Create Test Scenario & Test Script |  |  | 3
| System Integration Test (SIT) |  |  | 5 | 1 | 1
| User Acceptance Test (UAT) |  | 0.25 | 2.5 | 2 | 2
| Perform Security Test | [5 empty] | 3
Final Preparation | Develop Deployment Plan & QA Process | Sign-Off GO Live |  | 1
| Prepare and setup Production Environment |  |  | 0.5
| Production Deployment (Go-Live) |  |  | 0.5
| Go-Live Sign-Off |  | 0.25
Project Closure | Support After Go-Live
Total |  |  | 8 | 22 | 30 | 37 | 3 | 100
| Junior = 8,500 per day | [6 empty] | Digital Rev
| Senior = 14,000 per day | Rev/ Day | 14000 | 14000 | 14000 | 8500 | 8500
|  | Rev (BD Phase) | 7000 | 14000 | 0 | 0 | 0 | 21000
|  | Rev (Development Phase) | 105000 | 294000 | 420000 | 314500 | 25500 | 1159000
1180000
Digital Cost
|  | Cost/ Day | 6200 | 6200 | 6200 | 6200 | 3500
|  | Cost (Development Phase) | 49600 | 136400 | 186000 | 229400 | 10500 | 611900 | 12
611900

## Timeline
โครงการ ENH-PTTEP-iCMS 2026 Enhancement
ระยะเวลาโครงการ 172 วัน
ENH-PTTEP-iCMS 2026 Enhancement
Project Activity | Role | M1 |  |  |  | M2 |  |  |  | M3 |  |  |  | M4 |  |  |  | M5 |  |  |  | M6 |  |  |  | M7
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Project Preparation
- Kick Off Meeting | PM, BA, Dev, User
Requirement + Design
- Prepare/Review Requirement & Design | PM, BA, Dev, User
- Confirm Requirement & Design | PM, BA, Dev, User
- Requirement & Design Sign Off | PM, BA, Dev, User
Development
- Development | Dev
Testing
- Prepare Test Script | BA, Tester
- Integration Test and Unit Test | BA, Tester
- User Acceptance Testing | PM, BA, Tester, User
System Preparation
- Update User Manual | Security
- Security Scan/ Source Code Review | Security
- Production Installation & Setting | PM, Infra. Team
- Go-Live / Go-Live Sign Off | PM, User
Support After Go-live
- Support After Go-live | BA, PM, Dev, User

## Timeline 2 POT
โครงการ ENH-PTTEP-iCMS 2026 Enhancement
ระยะเวลาโครงการ 172 วัน
ENH-PTTEP-iCMS for Job Family Restructuring
Project Activity | Role | M1 (Mar) |  |  |  | M2 (Apr) |  |  |  | M3 (May) |  |  |  | M4 (Jun) |  |  |  | M5 (Jul) |  |  |  | M6 (Aug) |  |  |  | M7 (Sep) |  |  |  | M8 (Oct) |  |  |  | M9 (Nov)
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Project Preparation
- Kick Off Meeting | PM, BA, Dev, User
Requirement + Design
- Prepare/Review Requirement & Design | PM, BA, Dev, User
- Confirm Requirement & Design | PM, BA, Dev, User
- Requirement & Design Sign Off | PM, BA, Dev, User
Development
- Development | Dev
Testing
- Prepare Test Script | BA, Tester
- Integration Test and Unit Test | BA, Tester
- User Acceptance Testing | PM, BA, Tester, User
System Preparation
- Security Scan/ Source Code Review | Security
- Production Installation & Setting | PM, Infra. Team
- Go-Live / Go-Live Sign Off | PM, User
Support After Go-live
- Support After Go-live | BA, PM, Dev, User
ENH-PTTEP-iCMS 2026 Enhancement
Project Preparation
- Kick Off Meeting | PM, BA, Dev, User
Requirement + Design
- Prepare/Review Requirement & Design | PM, BA, Dev, User
- Confirm Requirement & Design | PM, BA, Dev, User
- Requirement & Design Sign Off | PM, BA, Dev, User
Development
- Development | Dev
Testing
- Prepare Test Script | BA, Tester
- Integration Test and Unit Test | BA, Tester
- User Acceptance Testing | PM, BA, Tester, User
System Preparation
- Update User Manual | Security
- Security Scan/ Source Code Review | Security
- Production Installation & Setting | PM, Infra. Team
- Go-Live / Go-Live Sign Off | PM, User
Support After Go-live
- Support After Go-live | BA, PM, Dev, User