## Resource
Team Information |  |  |  |  | Total Manday (Day)
No. | Name | Type | Role | Level | Planned (Day) | Manday Rate (Baht)
1 | คุณภฤศธร ใต้เวชศาสตร์ | PTT Digital | Project Manager | Senior | 38 |  | 14000 | 532000
2 | คุณพจนารถ สระหนองห้าง | Outsource | System Analyst | Officer | 58 |  | 8500 | 493000
3 | คุณณัฐ วัฒนากิจจากุล | Outsource | Business Analyst | Officer | 57
4 | คุณอานนท์ จูงใจ | Outsource | Developer | Officer | 144 |  | 14000 | 2016000
5 | คุณชนินทร์กานต์ วังคำ | Outsource | Developer | Officer | 89
6 | คุณเมธี อิศรานุวัต | Outsource | Tester | Officer | 44
7 | คุณกรรณิการ์ เพ็งพล | Outsource | Technical Review | Officer | 4
8 | คุณชาญวุฒิ ช่างการ | Outsource | Security | Officer | 4
9 | คุณสถาพร หัสกรรณ์ | Outsource | Infrastructure | Officer | 4 |  |  | 3041000
10 | คุณพัชร มีสวัสดิ์ | Outsource | DevOps | Officer | 4
Other Information |  | Total Amount (Baht)
1 | Hardware | -
2 | Software | -
3 | License | -
4 | Allowance | -
5 | ค่าดำเนินโครงการโดยที่ปรึกษาภายนอก | -
6 | DevOps Service
หมายเหตุ ถ้ามีประเภทค่าใช้จ่ายอื่นๆ เพิ่มเติมใน Project เพิ่ม Row ได้
1000000
1190000
[7 empty] | Total | 2190000
Note on G3: Pimsupak Tammalakkhana: ให้ใส่ Cost หาก PM ไม่ทราบให้ว่างไว้
Note on B20: Pimsupak Tammalakkhana: ระบุค่าเดินทาง หาก Project ไหนต้องย่อยรายละเอียดการเดินทางแยก Sheet Declare มาอีกอัน

## Total
Digital Rev (BD Phase) | 28000
Digital Rev (Development Phase) | 3972000
ค่าเบี้ยเลี้ยง/ค่าเดินทาง | 0
Total | 4000000
ค่าเดินทาง | จำนวนครั้ง | ครั้งละ | รวมค่าเดินทาง
- | 0 | 2500 | 0
0
0
|  | Total | 0
ค่าเบี้ยเลี้ยง | จำนวนครั้ง | ครั้งละ | รวมค่าเบี้ยเลี้ยง
- | 0 | 600 | 0
- |  | 600 | 0
- |  | 600 | 0
|  | Total | 0
งวดการชำระเงิน PTT >> PTT Digital | % | จำนวนเงิน
งวดที่ 1 : Requirement & Design | 40% | 1600000
งวดที่ 2 : Phase 1: Test & Go-Live | 30% | 1200000
งวดที่ 3 : Phase 2: Test & Go-Live | 30% | 1200000
| 100% | 4000000

## PTTDigital_Manday
โครงการ ENH-PTTEP-Digital Job Card Phase 5
(ระยะเวลาโครงการ ….270…. วัน) |  |  | Sr1 | Of1 | Of1 | Of1 | Of1 | Of1 | Of1 | Of1 | Of1 | Of1 | Of1
Phase | Details | Deliverables | PM | SA | Jr Dev | Jr Dev | Tester | BA | Technical Review | Security | Infrastructure | DevOps | App. Support
|  |  | Bharitsathorn T. | Potjanart S. | Anon Ju. | Chaninkarn W. | Maytee I. | Nat W. | Kannika P. | Chanvut C. | Sathaporn H. | Patchara M. | Name
Business Development | Gather Initial Requirements | Proposal | 2
Create Proposal & Project Plan
Vendor Selection
Impact analyst
Project Planning | Kick-Off Meeting |  | 6
Create Project Plan, Other Plans and Integrate to Project Plan
Monitoring
Progress Report
Prepare and setup Development Environment
Requirement Development | Get Requirement |  | 6 | 5 |  |  |  | 8
Create Business Blueprint
Peer Review Requirement Specification
Confirm Requirement Specification with Customer
Sign off Requirement Specification
Create Baseline for Design(CM)
Design | Peer Review Design Specification | Sign-Off Requirement Specification | 2 | 5 |  |  |  | 2
Clarify Design
Sign off Design Specification
Peer Review Technical Specification
Develop & Unit Test | Development & Unit Test
| 1.Build & Test Crane load test Form |  | 17 | 7 | 17 | 5 | 9 | 6
| 2.Build & Test Crane Pull Test Form |  |  | 7 | 11 | 10 | 9 | 6
| 3.Build & Test OverHead Line Form |  |  | 9 | 16 | 10 | 9 | 6
| 4. Build & Test Enh_Existing_Funtion_DJC#5 WHP, Transmitter, PSV |  |  | 18 | 100 | 64 | 17 | 29
SIT & UAT | Testing | Sign-Off UAT
Peer Review Software Implementation & Unit Test
Create Test Scenario & Test Script
| System Integration Test (SIT) |  | 1 | 1
| User Acceptance Test (UAT) |  | 1 | 1
Sign-Off UAT
Perform Security Test
EA Process
Create Baseline for Final Preparation
Final Preparation | Develop Deployment Plan & Readiness Checklist | Production Deployment | 2 | 5 |  |  |  |  | 2 | 2 | 2 | 2
Create release documents
Prepare Training Material / User Manual
Train The Trainer (TTT)
End User Training (EUT)
Prepare and perform Data migration/conversion
Prepare and setup Production Environment
Technical Training
Create Final Baseline
Project Closure | Go-live Support and Go-live Sign off | Sign-Off GO Live | 1 | [5 empty] | 2 | 2 | 2 | 2
Evaluate supplier/vendor
Survey Customer Satisfaction
Create Project closure report and Completion sign-off
Total |  |  | 38 | 58 | 144 | 89 | 44 | 57 | 4 | 4 | 4 | 4 | 0
หมายเหตุ Manday จำนวน 1 MD ของ App Support ใน activity Final Preparation จะไม่ได้ charge ลูกค้าเนื่องจากเป็นการเข้าไปเรียนรู้และ transfer system
| Junior = 8,500 per day | [12 empty] | Digital Rev
| Senior = 14,000 per day | Rev/ Day | 14000 | 8500 | 8500 | 8500 | 8500 | 8500 | 8500 | 8500 | 8500 | 8500 | 8500
|  | Rev (BD Phase) | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
|  | Rev (Development Phase) | 504000 | 493000 | 1224000 | 756500 | 374000 | 484500 | 34000 | 34000 | 34000 | 34000 | 0 | 3972000
4000000
0
Note on A20: Pimsupak Tammalakkhana: แล้วแต่ Project ว่าแบ่งส่งเอกสารเป็น 2 เล่ม Requirement และ Design หรือไม่

## Travel Cost
ค่าเดินทาง | จำนวนครั้งที่ไป |  | ราคา |  | จำนวนหน่วย | จำนวนการใช้งาน | รวม
| Requirement & Design | 0 | ค่าเดินทาง | 2500 | 0 | 0 | 0
| UAT | 0 | ค่าที่พัก | 2500 | 0 | 0 | 0
| Go-Live & Training |  | ค่าเบี้ยเลี้ยง | 600 | 0 | 0 | 0
| Total | 0 |  |  |  | รวมค่าเดินทาง | 0

## Project Timeline
Project timeline: 11 months periods |  | 2026-07-01 |  |  |  | 2026-08-01 |  |  |  | 2026-09-01 |  |  |  | 2026-10-01 |  |  |  | 2026-11-01 |  |  |  | 2026-12-01 |  |  |  | 2027-01-01 |  |  |  | 2027-02-01 |  |  |  | 2027-03-01 |  |  |  | 2027-04-01 |  |  |  | 2027-05-01 |  |  |  | 2027-06-01
No | Task | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4
1 | Project Preparation
2 | Project Kick-off
3 | Gather Requirement
4 | Analysis & Design
5 | Build & Test
6 | SIT | [13 empty] | SIT#1 | [22 empty] | SIT#2
7 | UAT | [16 empty] | UAT#1 | [21 empty] | UAT#2
8 | Deliver Project Document | [18 empty] | Training#1 | [21 empty] | Training#2
9 | Final Preparation & Production Deployment | [18 empty] | Deploy#1 | [21 empty] | Deploy#2
10 | Regression Test | [20 empty] | REG Test
11 | Go-live | [18 empty] | Go-Live#1 | [21 empty] | Go-Live#2
12 | Support after Go-live | [42 empty] | Support after Go-live
: งวดส่งมอบงาน